Thesis completion deadlines

Overall completion:
August 2019, with an aim to submit in the first week of August.

Individual chapter completion:

Introduction, conclusion and abstract: No work started on conclusion or abstract. Some text written for introduction. Completion expected during July.

MCRT technique: Nearly completed (99% done), various minor fixes needed. Has been submitted to supervisors. Completion expected by end of June.

Tissue ablation: Nearly completed (95% done), various minor fixes and small section on application of method to be written (100-200 words + figure). Has been submitted to supervisors. Completion expected by end of June.

Quasi-wave/particle MCRT: Mostly done (75%), some small simulations to be done 1-2 days work. Some text to be written on aforementioned simulations. Will be submitted to supervisors by w/e 1/6/19. Completion expected by end of June.

AmoebaMCRT: Around 25% of chapter written up. All coding completed, need to run model on experimental data. Simulations should take 1-2 weeks. Completion expected by end of June.

Fluorescent images: Nothing written up yet, though have some text from 1st year report. Theory and code mostly the same as previous chapter so will be a small “application” chapter. Completion expected by end of July.